## Dashboard
Planning Pack Dashboard
Generated | 2026-05-28
Recommended MVP | US rural land / homestead dossier in 3-5 counties
Storage stance | Postgres/PostGIS system of record; object storage for heavy raw assets
Build stance | Bottom-up: source registry -> evidence -> claims -> report -> API/UI
Metric | Formula/Value | Interpretation
Requirements count | 39 | Total traced requirements
Must requirements | 33 | Hard requirements
Critical risks | 7 | Highest-severity blockers
High risks | 12 | Material blockers
Must-have data sources | 8 | Required source categories
Backlog must items | 23 | Critical build tasks
Cost inputs tracked | 15 | Inputs for unit economics

## Requirements
Requirement ID | Domain | Requirement | Priority | Rationale | Acceptance Criteria
REQ-CORE-001 | Core | The system shall store every area with validated geometry and source/provenance metadata. | Must | Postgres/PostGIS | Area geometry can be queried spatially and has confidence/source fields.
REQ-CORE-002 | Core | The system shall support parcels, polygons, localities, watersheds, corridors, and generated candidates. | Must | Global-ready area model | Area type enum supports all MVP and future area categories.
REQ-CORE-003 | Core | The system shall store report runs as reproducible artifacts with source manifests. | Must | Reproducibility | A report run includes source versions, rule version, method versions, and timestamp.
REQ-SRC-001 | Source Registry | The system shall maintain a source registry before using any dataset. | Must | Data governance | Every dataset version references a source registry row.
REQ-SRC-002 | Source Registry | The system shall store license/entitlement attributes per source. | Must | Data rights | Display/export/cache/AI-use flags are available to policy checks.
REQ-SRC-003 | Source Registry | The system shall record failed source lookups as evidence. | Must | False negative prevention | Source failures appear in report unknowns.
REQ-SRC-004 | Source Registry | The system shall store immutable raw source snapshots where license permits. | Should | Reproducibility | Dataset version rows have checksums and storage URIs.
REQ-DATA-001 | Data Ingestion | The system shall validate CRS, geometry validity, row counts, and schema drift on ingest. | Must | Data QA | Ingest run stores validation metrics and warnings.
REQ-DATA-002 | Data Ingestion | The system shall preserve source-native attributes in JSON alongside normalized fields. | Should | Non-fragility | Source schema changes do not destroy unknown fields.
REQ-DATA-003 | Data Ingestion | The system shall support local/jurisdiction adapters. | Must | Expansion | New county/state sources can be added without core schema rewrite.
REQ-GEO-001 | Feature Extraction | The system shall compute flood/wetland intersection metrics for an area. | Must | MVP report | Evidence records include intersection area/percent.
REQ-GEO-002 | Feature Extraction | The system shall compute slope/elevation metrics. | Must | MVP report | Evidence/metrics include mean/max/percentile slope or buildable-area proxy.
REQ-GEO-003 | Feature Extraction | The system shall compute road/access proximity as proxy evidence only. | Must | Access caveat | Claim language states physical proximity does not prove legal access.
REQ-GEO-004 | Feature Extraction | The system shall compute nearest environmental regulated facilities where source data is available. | Should | MVP hazards | Evidence includes distance, facility ID, and source date.
REQ-EVID-001 | Evidence | The system shall store evidence separately from claims. | Must | Claim-first model | Claims join to evidence through claim_evidence table.
REQ-EVID-002 | Evidence | The system shall support negative evidence and source-failure evidence. | Must | Unknown handling | Reports distinguish none found vs source unavailable.
REQ-EVID-003 | Evidence | Evidence shall include method code and method version. | Must | Auditability | Every evidence row has method_code/method_version.
REQ-CLAIM-001 | Claims | Every claim shall link to at least one evidence item unless it is explicitly marked as a source failure/unknown claim. | Must | Trust | Claim-evidence link exists or unknown reason is present.
REQ-CLAIM-002 | Claims | Claims shall include confidence and severity bands. | Must | Risk reporting | Reports display both fields.
REQ-CLAIM-003 | Claims | High and critical claims shall generate verification tasks. | Must | User safety | Verification task row created.
REQ-RULE-001 | Rules | Hard gates shall execute before weighted scoring. | Must | Avoid false precision | Rule run output shows gate results before suitability band.
REQ-RULE-002 | Rules | Rulesets shall be versioned and immutable after report publication. | Must | Reproducibility | Report references rule_version_id.
REQ-RULE-003 | Rules | Suitability and confidence shall be reported separately. | Must | Trust | Report has both suitability band and confidence summary.
REQ-REP-001 | Reports | Reports shall include executive summary, red flags, unknowns, verification tasks, and source appendix. | Must | MVP output | Report template includes required sections.
REQ-REP-002 | Reports | Reports shall avoid definitive legal/title/survey/appraisal wording. | Must | Compliance | Safe-language lint passes.
REQ-REP-003 | Reports | Reports shall include machine-readable JSON output. | Should | Integrations | Report run has machine_json_uri.
REQ-QA-001 | QA | Golden parcels shall be maintained for regression tests. | Must | Quality | Regression suite includes known flood/wetland/access/zoning cases.
REQ-QA-002 | QA | All beta reports shall receive human review. | Must | Beta safety | Report status cannot become approved without reviewer action.
REQ-QA-003 | QA | The system shall log per-report cost metrics. | Must | Unit economics | Report run contains cost_metrics JSON.
REQ-SEC-001 | Security | Workspace-level access control shall protect user/report data. | Must | Security | All area/report queries scoped to workspace.
REQ-SEC-002 | Security | Data-license entitlements shall control display and export. | Must | Data rights | Export path checks source flags.
REQ-LEGAL-001 | Compliance | The MVP shall not use protected-class demographic variables for scoring. | Must | Fair housing risk | No protected-class inputs exist in MVP ruleset.
REQ-LEGAL-002 | Compliance | The MVP shall not position outputs as mortgage AVMs or appraisals. | Must | AVM risk | Report contains valuation disclaimer and no collateral-value output.
REQ-OPS-001 | Operations | Source onboarding shall require license review, QA, and documented caveats. | Must | Governance | Source status cannot be production without checklist.
REQ-OPS-002 | Operations | Reviewer overrides shall preserve original evidence and be audited. | Must | Audit | Audit event written for override.
REQ-API-001 | API | Report generation shall be asynchronous and idempotent. | Must | Scalability | POST /reports accepts idempotency key and returns job/report ID.
REQ-API-002 | API | API responses shall distinguish false, unknown, missing, and source failed. | Must | Semantic correctness | Response schema includes status fields.
REQ-GLB-001 | Global | Core area/evidence/claim schemas shall not hard-code U.S.-specific legal terms. | Should | Global readiness | Jurisdiction-specific fields live in adapters/metadata.
REQ-GLB-002 | Global | Global reports shall state diligence tier. | Should | Scope clarity | Tier 0/1/2 label appears in global outputs.

## Blockers
Risk ID | Category | Risk/Blocker | Severity | Likelihood | Mitigation | Owner | Stage
R-001 | Data | Parcel data license forbids report export or caching. | Critical | Medium | Perform vendor license audit before beta; implement entitlement gates. | Data/Legal | Pre-beta
R-002 | Data | County zoning data is stale, ambiguous, or not machine-readable. | Critical | High | Start with 3-5 counties; human QA; source citations; local adapter. | Data/Product | MVP
R-003 | Legal | System implies legal buildability or access. | Critical | Medium | Safe-language lint; disclaimers; verification tasks; legal review. | Legal/Product | MVP
R-004 | Legal | Fair housing/steering issue from residential area recommendations. | High | Medium | No demographic scoring; legal review before recommendation features. | Legal | Later
R-005 | Legal | Output becomes regulated AVM if valuation expands. | High | Medium | No mortgage valuation; legal review before valuation features. | Legal/Product | Later
R-006 | Technical | Postgres overloaded by raster-heavy workloads. | Medium | Medium | Store raw rasters as COG/object assets; derive summary metrics; async jobs. | Engineering | MVP
R-007 | Technical | Projection/CRS error causes wrong overlays. | Critical | Low/Medium | CRS validation tests; golden parcels; geometry pipeline review. | Geo Eng | MVP
R-008 | Technical | Source API outage silently becomes 'no issue found'. | Critical | Medium | Record source failure evidence; fail report or mark unknown. | Backend/Data | MVP
R-009 | Financial | Per-report cost exceeds price. | High | Medium | Instrument cost per report; concierge price test. | Product/Finance | MVP
R-010 | Product | Users want listing/comps search more than due diligence. | Medium | Medium | Manual beta interviews; compare willingness to pay. | Product | Phase 0
R-011 | Ops | Human review does not scale. | High | Medium | Risk-based review after golden tests; structured reviewer console. | Ops | Beta
R-012 | Data | Wetlands/flood layers treated as final regulatory determinations. | High | Medium | Caveats; professional verification tasks. | Product/Legal | MVP
R-013 | Data | Legal access cannot be inferred from maps. | Critical | High | Always phrase as access risk; title/easement verification task. | Product | MVP
R-014 | Data | Water rights/well viability too complex in first geography. | High | Medium | Select geography carefully; water module separate; cautious wording. | Product/Data | MVP
R-015 | Data | Mineral source data stale or rights severed. | Medium | High | Screen only; never assert mineral rights; cite source freshness. | Data/Product | Later
R-016 | Security | Owner/user data exposed across workspaces. | Critical | Low/Medium | RBAC, tenant scoping, audit, tests. | Engineering | MVP
R-017 | Architecture | Vendor schemas leak into core logic. | High | Medium | Adapter normalization; evidence layer boundary. | Engineering | MVP
R-018 | Architecture | UI computes conclusions client-side. | Medium | Medium | Server-authoritative claim/rules/report APIs. | Engineering | Productization
R-019 | Data | Commercial data terms prohibit AI processing. | High | Medium | License review includes AI-use flag. | Legal/Data | Pre-beta
R-020 | Trust | Single score hides missing data and uncertainty. | High | Medium | Suitability/confidence separation; unknown count visible. | Product | MVP
R-021 | Global | Global promise exceeds data/legal coverage. | High | High | Tiered global labels; no Tier 2 claims without local data. | Product | Later
R-022 | Technical | Report runs are not reproducible after source updates. | High | Medium | Dataset versions/source manifests/ruleset versioning. | Engineering | MVP
R-023 | Ops | Source update breaks golden parcel results. | Medium | High | Regression tests before source promotion. | Data QA | MVP
R-024 | Financial | Map/tile/egress costs spike under UI usage. | Medium | Medium | Cache tiles/assets; cap usage; budget alarms. | Engineering/Finance | Productization
R-025 | Legal | Report wording creates reliance/professional liability. | High | Medium | Legal review, E&O insurance review, cautious language. | Legal | Beta

## Data_Sources
Source ID | Name | Organization | Domain | Source Type | Geography | MVP Priority | URL | Use | Caveats
DS-001 | USGS The National Map | USGS | Terrain/elevation/hydro/boundaries | Public official | US | Must | https://www.usgs.gov/programs/national-geospatial-program/national-map | Elevation/slope and base layers | Physical screening only; check data vintages
DS-002 | FEMA NFHL | FEMA | Flood | Public official | US | Must | https://www.fema.gov/flood-maps/national-flood-hazard-layer | Flood hazard overlay | Modernized/effective-map limits; not all flood risk
DS-003 | USDA Web Soil Survey/SSURGO | USDA NRCS | Soils | Public official | US | Must | https://websoilsurvey.nrcs.usda.gov/ | Soil/septic/ag proxy | Not a substitute for site-specific test
DS-004 | National Wetlands Inventory | USFWS | Wetlands | Public official | US | Must | https://www.fws.gov/program/national-wetlands-inventory | Wetland/deepwater screening | Not jurisdictional delineation
DS-005 | USGS Water Data APIs | USGS | Water monitoring | Public official | US | Should | https://api.waterdata.usgs.gov/ | Streamflow/groundwater/water quality context | Monitoring proximity may be weak proxy
DS-006 | EPA ECHO | EPA | Environmental compliance | Public official | US | Should | https://echo.epa.gov/resources/echo-data/about-the-data | Regulated facilities/violations/enforcement | Nearby facility does not prove subject contamination
DS-007 | BLM MLRS | BLM | Mineral/land records | Public official | Federal lands/US | Later | https://www.blm.gov/services/land-records/mlrs | Mining claims/public land records | Does not resolve private mineral rights
DS-008 | USGS MRDS | USGS | Minerals | Public/stale official | US/global selected | Later | https://mrdata.usgs.gov/mrds/ | Mineral occurrence screening | Systematic updates ceased; treat as historical screening
DS-009 | National Zoning Atlas | NZA | Zoning | Nonprofit/open where available | US partial | Could | https://www.zoningatlas.org/ | Zoning baseline where available | Coverage incomplete
DS-010 | County GIS parcels | County | Parcels | Local official/varies | County | Must | Varies | Parcel geometry and local attributes | Approximate; not survey
DS-011 | County assessor | County | Assessor/tax | Local official | County | Must | Varies | Assessed value, tax year, situs | Schema/access varies
DS-012 | County recorder | County | Deeds/easements | Local official | County | Should | Varies | Recorded documents, easements, covenants | Often manual/search-limited
DS-013 | State well logs | State agency | Water/wells | State official | State | Should | Varies | Nearby well context | May not prove viability
DS-014 | State water rights | State agency | Water rights | State official | State | Later | Varies | Legal water-use screening | Complex and jurisdiction-specific
DS-015 | State geological survey | State agency | Geology/minerals | State official | State | Later | Varies | Geologic hazards/resources | Varies by state
DS-016 | OpenStreetMap/Overture | OSM/Overture | Roads/buildings/base map | Open community/open data | Global | Should | https://www.openstreetmap.org/ | Access/infrastructure proxy | Not authoritative for legal access
DS-017 | Commercial parcel vendor | Vendor | Parcels/ownership | Commercial | US/Canada or broader | Must | TBD | Normalized parcel/ownership data | License/cost blocker
DS-018 | Commercial comps/listings vendor | Vendor | Market | Commercial | Varies | Should | TBD | Market context | License/cost/export blocker
DS-019 | Commercial zoning vendor | Vendor | Zoning | Commercial | Varies | Could | TBD | Normalized zoning/allowed uses | Must verify with official local sources
DS-020 | NOAA climate/weather | NOAA | Climate/weather | Public official | US | Later | https://www.noaa.gov/ | Climate history/context | Not full forward-looking parcel risk
DS-021 | FCC Broadband Map | FCC | Broadband | Public official | US | Could | https://broadbandmap.fcc.gov/ | Broadband availability proxy | Coverage/provider claims may need verification
DS-022 | Census TIGER/ACS | Census | Boundaries/demographics | Public official | US | Later | https://www.census.gov/ | Admin boundaries; avoid protected-class scoring | Fair housing care
DS-023 | Local zoning ordinance PDFs | County/municipality | Zoning/legal text | Local official | Local | Must | Varies | Allowed use/minimum lot size/overlays | Hard to parse; source/date caveats
DS-024 | Title company/manual report | Title company | Title/access/easements | Professional/manual | Parcel | Later | TBD | Verification input | External professional source
DS-025 | Surveyor/manual report | Licensed surveyor | Boundary | Professional/manual | Parcel | Later | TBD | Boundary verification | External professional source

## Backlog
Epic | Backlog ID | Item | Owner | Priority | Phase | Dependencies | Acceptance Criteria
E01 | B-001 | Create source registry schema | Backend/Data | Must | Phase 1 | None | Source tables created and seed loaded
E02 | B-002 | Create Postgres/PostGIS core schema | Backend | Must | Phase 1 | None | DDL runs in dev DB
E03 | B-003 | Implement area geometry validation | Geo Eng | Must | Phase 1 | B-002 | Invalid geometry rejected or repaired with audit
E01 | B-004 | Seed public source registry | Data | Must | Phase 1 | B-001 | USGS/FEMA/USDA/USFWS/EPA/BLM sources present
E04 | B-005 | Build parcel ingestion adapter for target counties | Data | Must | Phase 2 | B-002 | Target county parcels loaded with lineage
E04 | B-006 | Build FEMA NFHL ingestion/overlay | Geo Eng | Must | Phase 2 | B-002 | Flood intersection evidence created
E04 | B-007 | Build NWI ingestion/overlay | Geo Eng | Must | Phase 2 | B-002 | Wetland intersection evidence created
E04 | B-008 | Build soils ingestion/lookup | Geo Eng/Data | Must | Phase 2 | B-002 | Soil evidence created
E04 | B-009 | Build elevation/slope pipeline | Geo Eng | Must | Phase 2 | B-002 | Slope metrics created
E04 | B-010 | Build EPA ECHO proximity adapter | Data | Should | Phase 2 | B-002 | Nearest regulated facilities evidence created
E05 | B-011 | Implement feature extraction job runner | Backend/Geo | Must | Phase 3 | B-003 | Async feature jobs complete and log costs
E06 | B-012 | Implement evidence service | Backend | Must | Phase 3 | B-002 | Evidence records can be created/queried
E06 | B-013 | Implement source failure evidence | Backend | Must | Phase 3 | B-012 | Failed source checks appear as evidence
E07 | B-014 | Implement hard-gate rules engine | Backend/Product | Must | Phase 4 | B-012 | Rules execute on evidence and output gates
E07 | B-015 | Implement confidence bands | Backend/Product | Must | Phase 4 | B-014 | Claims include confidence
E07 | B-016 | Implement red-flag taxonomy v0 | Product | Must | Phase 4 | B-014 | Claim codes documented and generated
E07 | B-017 | Implement verification task generator | Backend/Product | Must | Phase 4 | B-014 | High/critical claims create tasks
E08 | B-018 | Build Markdown report compiler | Backend/Product | Must | Phase 5 | B-017 | Report sections generated
E08 | B-019 | Build machine-readable JSON output | Backend | Should | Phase 5 | B-018 | JSON artifact generated and stored
E09 | B-020 | Build reviewer approval workflow | Backend/Ops | Must | Phase 5 | B-018 | Reports need approval before delivery
E13 | B-021 | Create golden parcel test set | QA/Product | Must | Phase 3 | B-005 | Regression parcels documented
E13 | B-022 | Safe-language linting | QA/Legal | Must | Phase 4 | B-018 | Forbidden wording detected
E12 | B-023 | Implement entitlement checks | Backend/Legal | Must | Phase 5 | B-001 | Restricted data cannot be exported
E10 | B-024 | Implement report API endpoints | Backend | Should | Phase 6 | B-018 | POST/GET reports working
E11 | B-025 | Build minimal report dashboard | Frontend | Could | Phase 7 | B-024 | User can view reports
E11 | B-026 | Build map asset viewer | Frontend/Geo | Could | Phase 7 | B-025 | Report maps visible
E12 | B-027 | Add billing/report credits | Backend/Product | Could | Phase 7 | B-024 | Pay-per-report flow works
E15 | B-028 | Define jurisdiction adapter interface | Architecture | Should | Phase 2 | B-002 | Adapter contract documented
E14 | B-029 | Legal review of disclaimers and output language | Legal/Product | Must | Pre-beta | B-018 | Approved language
E14 | B-030 | Data-license review workflow | Legal/Data | Must | Phase 1 | B-001 | License checklist complete

## Cost_Model
Category | Input | Initial Value | Unit | Importance | Notes
Data | Parcel vendor cost per parcel/report | Unknown | USD/report | Critical | Quote vendors; model tiers
Data | Comps/listing data cost | Unknown | USD/report | High | Optional MVP unless users demand market context
Data | Zoning vendor/API cost | Unknown | USD/report | High | May use local official sources + manual QA first
Compute | Spatial overlay runtime | TBD | seconds/report | Medium | Measure on 100 parcels
Compute | Raster slope processing cost | TBD | USD/report | Medium | Precompute where possible
LLM | Zoning/document extraction tokens | TBD | USD/report | High | Cache by ordinance/version
Human QA | Reviewer minutes per report | TBD | minutes/report | Critical | Measure in manual beta
Map | Tile/map asset generation cost | TBD | USD/report | Medium | Prefer cached/static report assets
Storage | Raw source archive storage | TBD | GB/month | Low/Medium | Object storage; version retention policy
Support | Support minutes per report | TBD | minutes/report | Medium | Track during beta
Legal | Compliance review allocation | TBD | USD/month | Medium | Budget before public launch
Insurance | E&O/professional liability | TBD | USD/year | Medium | Broker quote after MVP positioning
Revenue | Consumer report price | Hypothesis: 49-299 | USD/report | Critical | Test willingness to pay
Revenue | Pro plan price | Hypothesis: 199-999 | USD/month | Medium | Only after repeated usage
Revenue | Enterprise contract | Hypothesis: negotiated | USD/year | Later | After batch/API demand

## Decision_Gates
Gate | Decision | Required Evidence | Owner | Status
DG-001 | Choose first geography | Selection matrix + source audit | Product/Data | Open
DG-002 | Choose parcel data source | License/cost/coverage comparison | Data/Legal | Open
DG-003 | Approve schema | DDL review + test load | Engineering | Open
DG-004 | Approve MVP ruleset | Golden parcel regression tests | Product/QA | Open
DG-005 | Approve report language | Legal/compliance review | Legal/Product | Open
DG-006 | Approve beta pricing | Measured cost + customer feedback | Product/Finance | Open
DG-007 | Approve public beta | Source stability + QA metrics | Leadership | Open